## Read Me
SEMS - User Acceptance Testing workbook
Secure Event Management System, Universiti Poly-Tech Malaysia
How to use this workbook
1. | Test Cases holds the 48 test scenarios. Do not type in it: its Executed / Pass / Fail / Blocked / Pass rate columns are calculated from Results.
2. | Results: add one row per tester per test case (Tester ID, Role, TC ID, Result). Paste rows from the Google Form export here.
3. | Defect Log: add one row for every problem found. Link it to a TC ID. Keep the Status up to date.
4. | Survey: paste the Google Form response rows into columns A to S (same order as the form). The SUS score is calculated for you (0 to 100).
5. | Summary: shows pass rates, defects, SUS and whether each acceptance criterion is met. Nothing to type there.
6. | Type only in Results, Defect Log, Survey and the yellow numbers on Testers. Everything else is calculated, so leave it alone. The three data sheets start empty.
Result codes
Pass | The system did what the Expected result says.
Fail | The system did something different or broke. Log a defect.
Blocked | You could not run the case (missing data, earlier step failed). Say why in the comment.
Defect severity
Critical | Cannot continue, data is lost or exposed, or another role's data is visible. Must be fixed before acceptance.
Major | A main task fails or gives wrong results, but there is a workaround.
Minor | A small problem that does not stop the task (unclear message, awkward layout).
Cosmetic | Spelling, alignment or colour issues only.
Example rows (format only - do not copy into the data sheets)
Sheet | Example row
Results | Tester ID: T07 ¦ Name: Aina ¦ Role: Club Committee ¦ TC ID: CLB-04 ¦ Result: Fail ¦ Comment: Total shows RM 0.00 after deleting a row ¦ Date: 2026-11-02 ¦ Defect: D-004
Defect Log | D-004 ¦ 2026-11-02 ¦ T07 ¦ CLB-04 ¦ Club Committee ¦ Budget total wrong after removing a row ¦ Steps: add 3 rows, remove the 2nd ¦ Major ¦ Open
Survey | 2026-11-02 10:41 ¦ T07 ¦ Phone ¦ SUS answers 4,2,4,1,4,2,5,1,4,2 (gives SUS 82.5) ¦ UAT answers 4,4,5 ¦ open answers ¦ Recommend: Yes

## Summary
UAT summary
All figures are calculated from the Results, Defect Log and Survey sheets.
1. Test execution by role
Role | Test cases | Executions | Pass | Fail | Blocked | Pass rate
General
Club Committee
HEPA Officer
Admin
All roles
2. Test execution by priority
Priority | Test cases | Executions | Pass | Fail | Blocked | Pass rate
High
Medium
Low
3. Defects
Severity | Reported | Still open
Critical
Major
Minor
Cosmetic
'Still open' counts every defect that is not Closed or Won't fix. Rows with no severity are not counted.
4. Survey
Measure | Value
Respondents
Average SUS score (0 to 100)
SUS rating
Would recommend (Yes)
SUS bands: 80.3+ Excellent, 68+ Good (average or better), 51+ Below average, under 51 Poor (Sauro & Lewis).
Average score per UAT statement (1 to 5)
Statement | Average
UAT 1: The system does what I expected it to do for my role.
UAT 2: The messages and hints (errors, confirmations) were clear and helpful.
UAT 3: I trust this system with my personal information.
5. Acceptance criteria
Criterion | Target | Actual | Status
Overall pass rate | 85%
High-priority pass rate | 90%
Open Critical defects | 0
Open Major defects | 2
Average SUS score | 68
Testers who would recommend | 80%
Targets in blue are assumptions: agree them with your supervisor before testing starts. 'Executions' counts every Pass, Fail and Blocked row.
Overall

## Testers
Tester allocation
Suggested split for 50+ testers. Edit the yellow numbers; the total follows.
Role | Testers | Test cases to run | Time per tester (min)
Club Committee | 36 | GEN core (4) + GEN-01, GEN-10 + CLB-01 to CLB-15 | 45 to 60
HEPA Officer | 10 | GEN core (4) + HEP-01 to HEP-12 | 45 to 55
Admin | 4 | GEN core (4) + ADM-01 to ADM-11 | 40 to 50
Total |  | Every tester also answers the 18-question survey (about 5 minutes).

## Test Cases
TC ID | Role | Module | Scenario | Priority | All testers? | Preconditions | Steps | Expected result | Executed | Pass | Fail | Blocked | Pass rate
GEN-01 | General | Authentication | Register a new account with email verification | High | No | Club Committee testers only (HEPA and Admin testers get an account from the facilitator). A real email address you can open. Use dummy IDs, never your real IC number. | 1. Open the SEMS address and click Register. 2. Fill in every field. The role is Club Committee. Use a dummy ID such as AM2026000123. 3. Tick the Terms box and click Register. 4. Open the email and copy the 6-digit code. 5. Type the code on the verification screen. | The code email arrives within about a minute. After the correct code the account is created and you land on your role's dashboard.
GEN-02 | General | Authentication | Registration form validation | High | Yes | None. | 1. Open Register and click Register with everything empty. 2. Enter an invalid email (for example abc@), a password under 8 characters and a different confirmation password. 3. Leave the Terms box unticked. | Each problem is shown next to its own field in plain language. No account is created and you cannot continue until everything is fixed.
GEN-03 | General | Authentication | Sign in, sign out and a wrong password | High | Yes | An account you registered. Do NOT try a wrong password more than twice: five wrong attempts lock the account for 15 minutes. | 1. Sign in with your email and password, then log out. 2. Sign in again using your username instead of the email, then log out. 3. Try one deliberately wrong password. | Email and username both work. A wrong password shows a clear error that does not reveal whether the account exists. Remember me keeps you signed in only when ticked.
GEN-04 | General | Authentication | Forgot password | Medium | No | An account you registered. | 1. On the login page click Forgot password?. 2. Enter your email, then the 6-digit code you receive. 3. Choose a new password (8+ characters) and sign in with it. | Three clear steps. The code works for 10 minutes. The new password works and the old one no longer does.
GEN-05 | General | Authentication | Wrong code and resend | Medium | No | None. | 1. Start Forgot password and reach the code screen. 2. Type a wrong code and submit. 3. Click Resend code (wait for the 60-second timer first). | The screen says the code is wrong and how many attempts are left (5 maximum). A resent code works and the earlier code stops working.
GEN-06 | General | Usability | Dark mode and phone layout | Medium | Yes | A phone, or a narrow browser window. | 1. Click the sun/moon icon in the top bar. 2. Open the site on your phone (or shrink the window). 3. Visit your role's main pages. | The theme switches and is remembered. There is no sideways scrolling, the menu opens from the three-line icon, and all text is readable.
GEN-07 | General | Security | Pages other roles should not see | High | Yes | Signed in with your assigned role. | 1. While signed in, type the address of another role's page (for example a club member opens /admin or /hepa/review). 2. Log out, then press the browser Back button. | You are sent away from pages that are not yours and no data from them is shown. After logging out, protected pages ask you to sign in.
GEN-08 | General | Profile | Profile photo and change email | Medium | No | Signed in. | 1. Open Profile, click the camera icon and upload a JPG or PNG. 2. Open Change email, enter a new address and verify it with the code. | The photo appears in the top bar. The email changes only after the correct code; a wrong code is refused.
GEN-09 | General | Profile | Change password | Medium | No | Signed in with an account whose password you know. Use a throw-away password. | 1. Open Profile and find Change password. 2. Click Change password with the boxes empty, then type a wrong current password, then a new password that is too short or does not match its confirmation. 3. Enter the correct current password and a valid new password twice, then click Change password. 4. Sign out and sign in again with the new password. | Each mistake is explained next to its box (wrong current password, fewer than 8 characters, passwords not matching, new password same as current). After a correct change a notice appears and you stay signed in. The new password works and the old one does not.
GEN-10 | General | Security | Only club committees can register | High | No | Signed out. | 1. Open Register and look at the Role choices. 2. Read the note under Role. | Only Club Committee is offered, with a note that HEPA officer accounts are created by the administrator. There is no way to register as HEPA Officer or Admin.
CLB-01 | Club Committee | Dashboard | Dashboard and statistics | High | No | Signed in as a club committee member. | 1. Open the dashboard. 2. Click a statistic card such as Draft. | Five statistics (Draft, Under Review, Requires Changes, Approved, Rejected) match My Proposals. Clicking a card filters the table. The Create Proposal button is easy to find.
CLB-02 | Club Committee | Create proposal | Step validation | High | No | None. | 1. Click Create Proposal. 2. Click Next without typing anything. | Required fields are flagged with helpful messages, the first problem gets focus, and you cannot move on.
CLB-03 | Club Committee | Create proposal | Steps 1 to 3: event, organizer, schedule | High | No | Use the sample data sheet from your facilitator. | 1. Fill Event Information and click Next. 2. On Organizer Information check that Organiser (Penganjur) starts with your club name, then fill Applicant Name, Student ID, Position and Phone Number. Try a phone number such as abc first. Click Next. 3. On Venue & Schedule try a past date, then an end time earlier than the start time, then correct them. | An invalid phone number, a past date and an end time before the start are refused with a clear message. With valid data Next works and completed steps show a tick.
CLB-04 | Club Committee | Create proposal | Budget table | High | No | Reached the Budget step. | 1. Add at least three items with quantity and unit price. 2. Change a quantity, then remove one row. 3. Type an item price but leave its name empty. | Row totals and Total Requested Budget update immediately and are arithmetically correct. The incomplete row shows an error.
CLB-05 | Club Committee | Create proposal | Document upload | High | No | Two small PDF files and one .exe or .zip file. | 1. Drag a PDF into the upload area. 2. Add the .exe file. 3. Use Preview, change a file's type, then Remove one. | The PDF appears as a card. The unsupported file is refused with a clear message. Preview opens the file. A Proposal Document is required to continue.
CLB-06 | Club Committee | Create proposal | Save a draft and continue later | High | No | Part of the form filled in. | 1. Click Save Draft. 2. Leave the page, open My Proposals and click the pencil icon on the draft. | A 'Draft saved' message appears. The draft reopens with everything you entered, and uploaded files are kept.
CLB-07 | Club Committee | Create proposal | Review and submit | High | No | A complete draft. | 1. Go to step 6 and read the summary. 2. Click Submit Proposal without ticking the confirmation box. 3. Tick the box, submit and confirm. | The summary matches what you typed. You must tick the confirmation. After submitting you see a success message and the status is Submitted.
CLB-08 | Club Committee | My Proposals | Search, filter, sort and pages | Medium | No | More than 5 proposals (your facilitator seeds extra). | 1. Search by name or proposal ID. 2. Filter by status, change the sort order, then use the page arrows. | The table reacts correctly each time and says clearly when nothing matches.
CLB-09 | Club Committee | My Proposals | Delete a draft | Low | No | A draft you created. | 1. Click the bin icon on a draft and confirm. | A confirmation appears first. The draft disappears. Submitted proposals have no delete option.
CLB-10 | Club Committee | Tracking | Interactive status timeline | High | No | At least one submitted proposal. | 1. On the dashboard find Proposal Tracking and choose a proposal. 2. Click each stage of the timeline. | Every stage shows a date, time and who did it, and the panel text matches the stage you clicked.
CLB-11 | Club Committee | Proposal details | Proposal details page | Medium | No | A submitted proposal with a document. | 1. Open a proposal from the list. 2. Check each section and use Preview and Download on a document. | Event, Organizer, Schedule, Budget, Documents, Review History and Audit Activity are all present and correct. Documents open and download.
CLB-12 | Club Committee | Review | Action Required after a query | High | No | Your facilitator has seeded a proposal with status Query. | 1. Open the queried proposal. 2. Read the Action Required box and click View Query. | An Action Required box shows HEPA's request. View Query shows the full text. Edit Proposal and Resubmit buttons are available.
CLB-13 | Club Committee | Review | Edit and resubmit | High | No | The queried proposal above. | 1. Click Edit Proposal and change something requested (for example add a budget row). 2. Go to the last step, tick the box and click Resubmit Proposal. | HEPA's request stays visible while you edit. After resubmitting the status is Resubmitted and the version number goes up.
CLB-14 | Club Committee | Post-event report | Submit and update a report | Medium | No | An approved event (seeded). | 1. Open Post-Event Report and click Submit report. 2. Try saving empty, then fill attendance, spending and summary and save. 3. Open the same report again and update it. | Empty fields are flagged. After saving, the event moves to Submitted reports. The update is saved.
CLB-15 | Club Committee | Notifications | Notifications for HEPA decisions | Medium | No | HEPA has acted on one of your proposals. | 1. Click the bell icon and open a notification. | Decisions (approved, rejected, query) are listed and open the right proposal. The badge clears after viewing.
HEP-01 | HEPA Officer | Dashboard | Dashboard overview | Medium | No | Signed in as a HEPA officer. | 1. Open the dashboard and compare the numbers with Proposal Review. | Pending Review, Queried, Approved This Month and Rejected This Month are shown and make sense. Needs your attention lists the most urgent proposals.
HEP-02 | HEPA Officer | Proposal review | Review queue and filters | High | No | Several pending proposals (seeded). | 1. Open Proposal Review. 2. Use search, status, budget, event date and sort. | Cards show event, club, date, budget, submission date, status and a priority badge with a reason. Every filter narrows the list correctly and Clear filters resets it.
HEP-03 | HEPA Officer | Proposal review | Open a proposal in the side panel | High | No | A proposal with status Submitted. | 1. Click a card or its Review Proposal button. 2. Scroll through the panel, then close it and look at the card again. | The panel shows facts, budget, documents and history. The status changes to Under Review automatically.
HEP-04 | HEPA Officer | Proposal review | Preview a document | Medium | No | A proposal with an uploaded PDF. | 1. In the panel click Preview on a document. | The document opens in a new tab and is readable.
HEP-05 | HEPA Officer | Proposal review | Move through the queue | Medium | No | At least three proposals in the list. | 1. Open a proposal and use the Next and Previous arrows in the panel header. | The panel switches proposals and shows the position (for example 2 of 5). Arrows are disabled at either end.
HEP-06 | HEPA Officer | Decisions | Query a proposal | High | No | A pending proposal. | 1. Click Query. 2. Check the pop-up shows proposal, club and ID. Try sending with an empty box. 3. Write what needs changing and click Send Query. | Sending empty is blocked with a message. After sending, a green notice confirms it, the status becomes Query, and the panel moves to the next proposal.
HEP-07 | HEPA Officer | Decisions | Reject a proposal | High | No | A pending proposal. | 1. Click Reject. 2. Try to confirm without a reason, then enter a reason and click Reject Proposal. | A reason is required. A confirmation notice appears and the status becomes Rejected. The club can read your reason.
HEP-08 | HEPA Officer | Decisions | Approve with the three-signature confirmation | High | No | A pending proposal. | 1. Click Approve and read the summary. 2. Try to approve with none, then only two, of the three signature boxes ticked (Penasihat / BHEP, Setiausaha ATAP Kolej, Pengarah). 3. Tick all three and click Approve Proposal. 4. Open the Calendar, then the proposal's full page. | The Approve button stays disabled until all three boxes are ticked. After approval a notice appears, the event shows on the Calendar, and the full page says who confirmed the signatures and when.
HEP-12 | HEPA Officer | Official form | Generate the BHEP.ML.01.04A-00 form | High | No | A submitted proposal with an itemised budget. | 1. On the proposal (full page or side panel) click Generate form. 2. Compare items 1 to 11 with the proposal: Nama Pemohon, No ID Pelajar, Penganjur, Tarikh and Lokasi Program, Bil Peserta, Objektif, Jawatan, No. H/P and the Tarikh beside item 11. 3. Check the Untuk Kegunaan Pejabat box, then page 2 (Lampiran A). 4. Click Print / Save as PDF and save it as a PDF. | The form matches the paper original and the proposal's details. Item 11's date is the date the club submitted. The office box (including Bajet Dimohon) is blank for signatures. Lampiran A lists the budget items and the correct total. The PDF has two A4 pages with no menus or buttons.
HEP-09 | HEPA Officer | Proposal details | Full proposal page | Medium | No | A decided proposal. | 1. Open the proposal's full page and read the timeline, review history and audit activity. | Every stage shows who did it and when. Actions you took are recorded.
HEP-10 | HEPA Officer | Approved events | Approved events list | Medium | No | Several approved events. | 1. Open Approved Events. 2. Search, filter by status and dates, and page through. | Approved (and cancelled) events are listed with club, date, venue and budget. Filters and paging work.
HEP-11 | HEPA Officer | Reports | Reports, charts and export | Medium | No | Some proposals decided. | 1. Open Reports and change the date range. 2. Hover over bars, then switch a chart to Table view. 3. Use Export for CSV and Print. | Four charts and a summary update with the range. Tooltips and table view show the same numbers. The CSV opens in Excel and Print shows a clean page.
ADM-01 | Admin | Dashboard | Dashboard and date range | High | No | Signed in as an admin. | 1. Read the statistics, charts and activity feed. 2. Change the date range. | Total Users, Total Clubs, Active Events and Pending Proposals are shown. Charts and the activity feed follow the range. Feed items read clearly (for example Proposal approved, ICT Club, 2 minutes ago).
ADM-02 | Admin | Dashboard | Export and print | Medium | No | Some activity exists. | 1. Open Export and download the analytics CSV and the activity CSV. 2. Choose Print / Save as PDF. | Both files open correctly in Excel with sensible columns. The printed page hides menus and is readable.
ADM-03 | Admin | Users | Create a user and change a role | High | No | None. | 1. Open Users and add a new HEPA Officer account (HEPA officers cannot register themselves). 2. Change that user's role, then try to change your own role. | The user is created and can sign in. The role change is saved. You are not allowed to change your own role.
ADM-04 | Admin | Users | Deactivate, reactivate and reset password | High | No | A second tester or a spare account. | 1. Deactivate a user, then try to sign in as that user. 2. Reactivate the user and reset their password, then sign in. | A deactivated user cannot sign in and sees a clear message. After reactivation and reset the new password works.
ADM-05 | Admin | Clubs | Create a club and assign a member | Medium | No | A club committee account exists. | 1. Open Clubs and create a club. 2. Assign a committee member to it. | The club appears in the list. The member's proposals now show the club name.
ADM-06 | Admin | Proposals | Monitor proposals (read-only) | Medium | No | Proposals in different statuses. | 1. Open Proposals, use the filters and open one proposal. | The list filters correctly. The detail page has no Approve or Reject buttons for Admin.
ADM-07 | Admin | Proposals | Cancel an approved event | High | No | An approved event. | 1. Open the approved proposal and click Cancel Event. 2. Try to confirm without a reason, then give a reason and confirm. 3. Check the Calendar. | A reason is required. The event disappears from the Calendar and is shown as Cancelled, with HEPA's approval still on record.
ADM-08 | Admin | Audit logs | Audit log filters and paging | High | No | Some activity exists. | 1. Open Audit Logs. 2. Filter by user, role, action, module, result and dates, then page through. | Columns include time, user, role, action, module, target, IP address and result. Each filter works and an entry count is shown.
ADM-09 | Admin | Audit logs | Audit entry details | Medium | No | At least one entry. | 1. Click a row to open its panel. 2. Check the IP address, browser and details, then click Copy as JSON. | A side panel shows when, who, what, target, where and details. Copy as JSON confirms with a notice.
ADM-10 | Admin | Audit logs | Export the audit log | Medium | No | Some entries. | 1. Apply a filter, click Export CSV and open the file. | Only the filtered entries are downloaded and the file opens correctly in Excel.
ADM-11 | Admin | Settings | Upload rules are enforced | Medium | No | A club account to test uploading. | 1. Open Settings and lower the maximum upload size or remove an allowed file type, then save. 2. As a club member, try to upload a file that now breaks the rule. | The upload is refused with a clear message. Restoring the setting allows it again.

## Results
Tester ID | Tester name | Role | TC ID | Result | Comment | Date tested | Defect ID

## Defect Log
Defect ID | Date reported | Reported by (Tester ID) | Related TC ID | Role | Summary | Steps to reproduce | Severity | Status | Screenshot / link | Fix notes | Date closed

## Survey
Timestamp | Tester ID | Device | SUS 1 | SUS 2 | SUS 3 | SUS 4 | SUS 5 | SUS 6 | SUS 7 | SUS 8 | SUS 9 | SUS 10 | UAT 1 | UAT 2 | UAT 3 | Most confusing / errors seen | One change | Recommend | Role (optional) | SUS score
Paste the Google Form response rows into columns A to S. The SUS score in column U is calculated. Scale: 1 = strongly disagree ... 5 = strongly agree; SUS items 2, 4, 6, 8 and 10 are negatively worded and the formula already reverses them.